## Sheet1
Task Name |  | Duration (days)
Software Developing
Renter App Design
| Discuss format with customer | 2
| Conduct research (1) | 10 | Smartsheet***
| Code booking interface | 30
| Build Scheduling Algorithm | 20
| Design Customer Profile Database | 10
| Design Payment Integration | 5
| Build Notification Systemm | 5
Driver App Design
| Discuss format with customer | 2
| Conduct research (1) | 10
| Code renter interface | 30
| Build vehicle inventory management system | 20
| Integrate payment System, and renter profile database | 5
Miscellaneous
| Build advertisement system within app | 10
| User verification | 10
Testing
| Prototyping and testing | 20
| debugging | 10
Marketing
| Conduct marketing research (1) | 10
| Discuss ad style with customer | 2
| Create ad lines | 20
| integrate ad lines within app | 5
Legal
| Conduct legal research (1) | 10
| Consult legal professionals | 10
| Prepare to Attain licensure | 5
| Intergrate customer and renter safety measures | 5
| Create protective legal documents | 15
| Integrate new program with existing customer insurance | 20